## Tender Query Schedule
TENDER QUERY SCHEDULE
Limestone Creek Estate Development, Yeppoon ¦ Job No. 5614 ¦ RFQ: Sewer, Water & Stormwater Reticulation
From: Tricore Civil Services Pty Ltd To: McIntosh Civil (Attn: Ben McIntosh / Chris Abad) Date: [DATE] Rev: A
Responses are required prior to tender close. Pricing submitted is qualified against the assumptions stated in the 'Tricore assumption pending response' column.
Ref | Category | Priority | Query | Tricore assumption pending response | Cost impact | McIntosh Civil response | Date responded
TQ-01 | Documentation | HIGH | No geotechnical report has been issued with the tender documents. Please provide the geotechnical investigation for the site, including rock levels, groundwater levels and trench stability data. | Rates assume excavation in ordinary material with conventional trench support. No allowance for rock excavation, unsuitable material or dewatering beyond nominal. | Significant
TQ-02 | Quantities | HIGH | Subsoil drainage quantities on the Trunk Road Section C and Stages 1 & 2 stormwater BOQ tabs return broken cell references and show no quantity. Please issue corrected quantities. | Rates provided; quantities carried at NIL. Item to be remeasured on award. | Moderate
TQ-03 | Scope | HIGH | Please confirm scope responsibility for the 3.6m x 0.9m and 3.6m x 1.2m RCBC — specifically whether supply, delivery, unloading and cranage of the box culvert units sit with Tricore or McIntosh Civil. | Priced as Tricore supply and install, including cranage and unloading. | Significant
TQ-04 | Standards | HIGH | The Water RFQ references SEQ Water standards. The project is within Livingstone Shire Council, which is not SEQ Water territory. Please confirm the applicable water authority standard and specification. | Priced to CMDG (Capricorn Municipal Development Guidelines) as shown on the drawings. | Moderate
TQ-05 | Scope | HIGH | Item 6.5.5 'Connect to existing Manhole' is described as by Livingstone Shire Council, yet appears as a priced line in the sewer BOQ. Please confirm whether this work is in Tricore's scope. | Nominal allowance carried. Excluded if Council-performed. | Minor
TQ-06 | Design | HIGH | Please provide structural details for the culvert base slab (1,072 m2) and the two 64m cast in-situ headwalls, including slab thickness, concrete grade and reinforcement schedule. | Priced on an assumed ~200mm slab with nominal reinforcement. Subject to adjustment on receipt of details. | Significant
TQ-07 | Design | MEDIUM | Custom grated junction pits are described as 'including Structural Design'. Please confirm whether structural design and RPEQ certification of these pits is Tricore's responsibility or is provided by the Principal. | Priced including an allowance for structural design and certification. | Moderate
TQ-08 | Scope | MEDIUM | Please confirm the interface for bulk earthworks. Tricore has assumed all service corridors are delivered at design subgrade level, trafficable and free-draining, prior to commencement of trenching. | Priced on that basis. Bulk earthworks, cut/fill and platform preparation excluded. | Moderate
TQ-09 | Scope | MEDIUM | Please confirm that traffic control and traffic management for all works, including works within Adelaide Park Road for the lead-in main, is provided by McIntosh Civil at no cost to Tricore. | Traffic control excluded from Tricore's pricing. | Moderate
TQ-10 | Scope | MEDIUM | Bio-retention basins: Tricore has priced pipework and pits only. Please confirm that basin earthworks, filter media, sand transition layer, aggregate drainage layer, planting and establishment are by others. | Basin earthworks and all media layers EXCLUDED. Pipe and pit only. | Moderate
TQ-11 | Provisional | MEDIUM | Please confirm the status of the Lead-In watermain to Adelaide Park Road (Section 9, 402m of 250mm PVC PN16) — whether it is to be priced as a firm item or remains provisional. | Priced and included as a separate provisional section within Stages 1 & 2. | Significant
TQ-12 | Provisional | MEDIUM | Disinfection of watermains and connection to existing watermains are nominated 'By Relevant Council — Provisional'. Please confirm scope, and whether Council fees are included in Tricore's price. | Nominal allowance carried. Council fees and charges excluded. | Minor
TQ-13 | Quantities | MEDIUM | Provisional item 'Allowance for Excavation and Installation in water-charged ground' appears in the sewer BOQ with no quantity. Please advise the quantity to be priced. | Extra-over rate provided; no quantity carried, therefore nil contribution to the tender sum. | Significant
TQ-14 | Programme | MEDIUM | Please provide the construction programme, including stage release dates and required durations for each of Trunk Road Section C, Stages 1 & 2, and Stages 3-6. | Priced assuming continuous access and a logical sequence with no acceleration or out-of-hours work. | Moderate
TQ-15 | Commercial | MEDIUM | Please provide the proposed subcontract terms, including payment terms, retention, liquidated damages, insurance requirements and back-charge provisions. | Pricing excludes any allowance for liquidated damages or abnormal contractual risk. | Moderate
TQ-16 | Documentation | LOW | Please provide the project technical specification. Only drawings and BOQ have been issued; the RFQ notes further documentation is available on request. | Priced to CMDG standards and the notes shown on the Land Dynamics drawings. | Moderate
TQ-17 | Quantities | LOW | The Stage 3-6 sewer BOQ contains a duplicated item reference (6.5.4 appears twice, for 33¾° bends and for 'Connect to existing Manhole'). Please confirm numbering. | Both lines priced as separate items per their descriptions. | Nil
TQ-18 | Scope | LOW | Please confirm responsibility for survey set-out and as-constructed survey / asset data capture for the completed services. | Survey set-out and as-constructed survey excluded from Tricore's pricing. | Moderate
TQ-19 | Site | LOW | Please confirm the site establishment arrangements available to Tricore, including laydown areas, site amenities, water supply and power, and whether these are provided by McIntosh Civil. | Priced assuming reasonable laydown adjacent to the works and shared site amenities. | Minor
TQ-20 | Scope | LOW | Please confirm responsibility for trench reinstatement within the road reserve — specifically whether pavement replacement over the trench is Tricore's scope or McIntosh Civil's. | Trench backfill to subgrade only. Pavement, kerb & channel and asphalt excluded. | Significant
Note: Tricore's tender pricing is qualified against the assumptions in column E. Where a response alters an assumption, Tricore reserves the right to adjust its price accordingly.